## Slide 1
V 2.0 July 2024
How to manage risks in your UK PACT project
Guidance for UK PACT Delivery Partners

## Slide 2
Risk management on UK PACT projects
Purpose
This Guide is designed to help you complete the Full Proposal Risk Register template and to explain UK PACT’s requirements for managing and reporting on risks to your project.
What do we mean by risk
We use the following definition of ‘risk’: an uncertain event that, if it occurs, has an impact on objectives ​
The cause-and-effect definition gives clarity on the consequences of the risk occurring, which makes it easier to develop effective mitigations that target the cause and/or the impacts. This helps weigh the risk against the potential costs and benefits.
When considering the key risks as part of your proposal, it’s helpful to clearly identify what the cause and effect of the risk is. For example:
Risk of… (uncertain event) ​due to… (cause) ​resulting in… (effect or impact)​
Risk management is the process of identifying, assessing, treating, monitoring, and reporting risks.
Why focus on risk management
UK PACT aims to contribute to transformational change. The projects funded by UK PACT operate in complex environments, where risks range from political uncertainty, shifts in macroeconomic context, corruption, natural disasters, social inequity and exclusion of groups of stakeholders, engaging with reputationally contested industries, among others. Delivering interventions in this context requires taking risks.
This means that risk management is critical for UK PACT projects because if risks are not managed carefully, your project may not make effective progress and the opportunity to deliver transformational change could be missed, reduced or slowed.
Integrating proactive, systematic risk management into project design strengthens planning for project activities. This, in turn, ensures that activities have the highest chance of success and ensuring efficient use of project resources through the project cycle. All successful applicants will need to maintain a risk register and monitor changes in the project’s risk profile to ensure that risks are effectively mitigated and managed. This is a key part of project management to ensure successful delivery of UK PACT projects.

## Slide 3
Preparing a risk management plan for your full proposal
To prepare a good proposal for UK PACT funding, you will need to demonstrate that you understand the risks that might impact upon your project’s objectives, and to detail the plans in place to mitigate them.
Identify risks
1
Assess risks
2
Manage risks
3
Monitor risks
4
Applicants shortlisted to submit a full proposal are asked to outline an appropriate and comprehensive assessment of key risks to the project.
Your ability to demonstrate that risks to delivery have been identified and that appropriate, effective mitigation measures are clear is part of the scoring criteria for proposals.
Your assessment of key risks should cover the most critical sources of risk: threats to delivery, operational challenges, fiduciary, reputational, safeguarding and contextual/strategic barriers.

## Slide 4
1. Identify risks – risk categories
It is not practical to assess and manage all possible risks related to delivering your project successfully. You should prioritise critical risks which need the most attention. We recommend prioritising no more than 10 risks maximum. Typically, projects may track 3-5 risks, depending on the duration, scale, complexity of the project activities, context and stakeholders involved. The critical types of risk identified for UK PACT projects are listed below:
Risk category | Definition
External context | External contextual events/circumstances arise from the complex environments in which projects operate. External context (macro-economic, political landscape) can affect the implementation of project, though these uncertainties are outside the direct influence of implementing partners. Risks should relate directly to the impact on the project. Contextual risks have cross-cutting impacts on other risk categories.
Delivery | Risks relate to the effective delivery of the project including business/activity disruption, technical complexities of the project, scope creep, missed deliverables, undermine or prevent achievement of intended benefits, outputs, outcomes, impact.
Operational | Internal or external events/circumstances/procedures related to the implementing partner or consortium partner’s capacity, effective ways of working together, procedures, processes, tools, including resourcing, recruitment, coordination and management capacity challenges.
Fiduciary | Events/circumstances such as misuse or mismanagement of grant funds, aid diversion (fraud activity), cases of corruption or inefficient use and control of UK PACT resources/budget e.g. FX fluctuations.
Reputational | Events/circumstances that damage the reputation or credibility of UK PACT and FCDO with counterparts, the public, implementing partners, beneficiaries or any other stakeholder. As UK PACT is a publicly funded programme subject to higher level of public scrutiny, reputational risks are categorised independently, though there is often overlap with other categories, i.e., a delivery or fiduciary risk may also be a reputational risk.
Safeguarding | Events/circumstances that could harm people and the environment such as exploitation, abuse, harassment, violence, bullying, discrimination, social exclusion. This includes risk of sexual exploitation, abuse and harassment, child labour and modern forms of slavery.
Security | Events (threats) such as civil unrest, conflict, crime, terrorism, natural/physical disasters that effect the safety of personnel, partners, facilities etc. Where your project operates in high-severe security threat locations, we will expect a full risk assessment and security protocols built into the risk mitigations, should your proposal be successful.

## Slide 5
1. Identify risks
Determine which risks may affect project objectives – prioritise the most significant risks associated with implementing the project (usually approx. 5 risks), but make sure you consider the full range of risk categories, as appropriate to your project context, to ensure that your assessment is comprehensive. There is no limit, the number of risks to prioritise is indicative to help with priortisation.
Start by reviewing the project deliverables, activities, stakeholders and the assumptions behind your Theory of Change.
Risks can be identified in many ways, including:
Consult the team
Review previous experience / past projects
SWOT analysis – what are the existing barriers, threats, dependencies upon which activities rely?
Note: if successful, you may be asked to build out the risk register in more detail following provisional grant award. Through project implementation, risk management should be treated as an iterative process, meaning that you should continuously monitor for new and emerging risks and add those to the register, where applicable.

## Slide 6
2. Assess risks
As part of your full proposal, we ask you to assess the key risks identified. This involves qualitative analysis of the likelihood of the risk occurring and the impact on objectives if this were to happen.
A risk matrix that combines the likelihood and impact can be used to prioritise risks with an overall rating.
Likelihood | Definition | Probability Score | 
Rare | Would be a one-off event or require unique/exceptional chain of events to trigger; the type of event that might happen once every 10 years | 1 | <5%
Unlikely | Not impossible, but exposure is not anticipated to happen in normal circumstances over lifetime of project; occurrence would be unusual/unexpected | 2 | 6-20%
Possible | Some evidence that it will occur; frequency of exposure is occasional over lifetime of project | 3 | 21-50%
Likely | More likely than not to happen; exposure is anticipated over lifetime of project, but not a persistent | 4 | 51-80%
Almost Certain | About to or expected to occur; definitive signs that exposure will happen over lifetime of project, recurrence is frequent | 5 | >80%
Impact | Definition | Impact Score
Insignificant | Fairly negligible, <one week delay to deliverable or activity, <1% over/under budget, activity only impacted in one output | 1
Minor | Some delays to activity or deliverable/s two-four weeks over schedule, 1-10% over/under budget, activities and deliverables across more than one output affected somewhat | 2
Moderate | Over schedule for a deliverable/s by more than one month, 10-15% over/under budget, several milestones are negatively affected and there's potential for material impact on overall objectives/intended outcomes | 3
Major | Significant delays/non achievement to one or more deliverables, over schedule by more than one quarter, potential that milestones will not be complete by quarter end/ spend/budget for the FY will be impacted, and/or PACT or FCDO reputation somewhat negatively impacted. If safeguarding risk of physical/psychological harm, this is the minimum anticipated impact due to nature of harm on people. | 4
Severe | Deliverable/s are delayed by more than two quarters or are unable to be completed, >25% over/under budget, overall objectives and outcomes unlikely to be achieved, reputation likely negatively affected | 5

## Slide 7
3. Manage risks
  Once risks have been assessed, they can be mapped onto a risk matrix, which measures risk level by multiplying probability and impact. This helps guide the level of effort/resources to be allocated for the risk response.
  The combined risk rating shows as minor, moderate, major or severe (shown in Figure 1).
  The risk rating should be managed – either through active monitoring for low-rated risks or taking active steps to avoid, reduce or mitigate (see Figure 2).
  When designing risk mitigations, the purpose is to move the rating of the risk down the axes of the risk matrix, either by:
  Reducing the likelihood of the risk occurring in the first place
  Reducing the impact it will have if it does occur
  Reducing both the likelihood and impact – take steps to avoid the risk by changing design of the project to remove the source of risk
  Risk mitigations should be:
  Integrated into the execution of the project
  Assigned to an owner responsible for actioning
  Specific and time-bound where possible, with deadlines set for achieving key steps
  Specific and broken down into achievable tasks
Likelihood | Almost certain | 5 | Moderate | Major | Severe | Severe | Severe
 | Likely | 4 | Minor | Moderate | Major | Severe | Severe
 | Possible | 3 | Minor | Moderate | Major | Major | Severe
 | Unlikely | 2 | Minor | Minor | Moderate | Moderate | Major
 | Rare | 1 | Minor | Minor | Minor | Minor | Moderate
 |  |  | 1 | 2 | 3 | 4 | 5
 |  |  | Insignificant | Minor | Moderate | Major | Severe
 |  |  | Impact |  |  |  | 
Likelihood | Almost certain | 5 | Mitigate | Reduce | Avoid | Avoid | Avoid
 | Likely | 4 | Accept | Mitigate | Reduce | Avoid | Avoid
 | Possible | 3 | Accept | Mitigate | Reduce | Reduce | Avoid
 | Unlikely | 2 | Accept | Accept | Mitigate | Mitigate | Reduce
 | Rare | 1 | Accept | Accept | Accept | Manage | Mitigate
 |  |  | 1 | 2 | 3 | 4 | 5
 |  |  | Insignificant | Minor | Moderate | Major | Severe
 |  |  | Impact |  |  |  | 
Figure 1
Figure 2

## Slide 8
Risk Registers
Full details and guidance on completing the Risk Register template are found in the guidance tab in the Risk Register Annex. Implementing partners should record and track the following details:
Information | Description | Example
Risk title | Keyline summary of the risk | E.g. Media criticism due to report that shows increased emissions within projec
Risk category | The type of risk | E.g. This is a reputational risk because the impact of media criticism would be damage to the brand’s reputation
Description | Full details on the cause/s of the risk event and the impacts should this occur | E.g. There is concern that publicly available data could be interpreted as showing deforestation within the project area since PACT’s involvement began
Mitigation strategy | Detailed information on actions or the response, with steps and timings | E.g. PACT to design defensive messaging document outlining reasoning and response
Risk rating | Decided by the assigned impact and likelihood ratings | E.g. – impact rating severe, likelihood rating unlikely
Responsible | The person responsible for the mitigation of the risk | E.g. PACT Comms Team
Due date for action | Date of next review the risk ratings and mitigation measures | E.g. Defensive messaging to be in place before the second phase of project activities commence

## Slide 9
4. Monitor and report risks - Risk management during project implementation
Risk management activities should be performed, recorded, and monitored and updated throughout the lifecycle of the grant, using the risk matrix template.
Risk updates will be a standing agenda item for your regular (at least monthly) meetings with UK PACT, where you should discuss any updates against your highest rated risks, significant changes to existing risks and flag any emerging (new) risks. We welcome a transparent and open culture to discussing risks and while implementing partners are ultimately responsible for the treatment of each risk, your UK PACT point of contact should be willing to discuss and assign ratings to risks where you are uncertain and request input or feedback.
Quarterly reporting
You will be asked to submit an updated Risk Register with the quarterly reporting schedule. When updating the Register, check the status is correct and amend any risks that have escalated into live issues or that are now closed.
All active risks must be reviewed for each reporting period: assess both the inherent and residual ratings are still accurate. Provide a succinct update on the status/progress of proposed mitigation measures for the period. Update the dates for next reviewing risks.
When providing the progress update, add a date for each entry. To avoid expanding the register for each update/quarter, simply add a date before your entry and keep the most recent entries at the top of the cell, so it is clear to the Grant Manager which is the most recent update
An example is provided in the Risk & Issue Register template